## Status Report - Brief
Week # | Date | Course Info | Target % | Paper % | Project % | Brief Summary of Status
1 | 2022-01-13 | Delayed |  |  |  | Courses delayed 1 week due to weather damage.
2 | 2022-01-20 | Class 1/19/23 |  |  |  | Watch video prior to class on Jan 19.
3 | 2022-01-27 | Final Proposal + Outline Due | 1%
4 | 2022-02-03 | Authentication Page | 10% | 10% | 15% | Installation and setup of tools and technologies 100% completed. Started developing authentication page for the project. We have added navigationbar for admin user, Login for admin, logout functionality. Authentication Page 20% completed.
5 | 2022-02-10 | Submit Draft Paper(Extension of Authentican Page) | 20% | 20% | 20% | Added a registration page for users, log-in for users, view profile page after login with user credentials, change password functionality for users after login, and logout functionality. Authentication page 70% completed.
6 | 2022-02-17 | Admin and user Functionality | 30% | 25% | 30% | We have added functionality that whenever a user registers from the registration page the request will go to the admin and the user is able to log in only when the admin accepts the request. And also we have added a form which adds product form in the project through which we can add the products. For now, it is enabled for admin and as well as users later we will enable the form based on the requirements.
7 | 2022-02-24 |  | 40%
8 | 2022-03-03 | Interim Report & Draft Paper | 50%
9 | 2022-03-10 | Spring Break
10 | 2022-03-17 |  | 60%
11 | 2022-03-24 |  | 70%
12 | 2022-03-31 | Submit Draft Paper | 80%
13 | 2022-04-07 | Easter Holiday
14 | 2022-04-14 |  | 90%
15 | 2022-04-21 | Electronic Copies | 100%
16 | 2022-04-28 | Final Presentation
| Notes: | Only make updates in light blue cells each week
For summary, just state major accompishments, not a detailed explanation of what you did
For summary, also include why behind Target % complete for Paper &/or Project
Formulas:
Date = [Date, row above]+7

## Status Report - Schedule
| Dec | Jan |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr
|  | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28
Week # | -1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16
Submit Proposal to Advisor | bar: Mar 10; Apr 7
Project Approval | bar: Jan 13 to Jan 20; Mar 10; Apr 7
Final Abstract | bar: Jan 27; Mar 10; Apr 7
Outline | bar: Jan 27; Mar 10; Apr 7
Weekly Status | bar: Jan 27 to Apr 21
Interim Report | bar: Mar 3 to Mar 10; Apr 7
Final Report & Draft Presentation (Electronic copies) | bar: Mar 10; Apr 7; Apr 21
Oral Presentation | bar: Mar 10; Apr 7; Apr 28
Final Presentation (Electronic) | bar: Mar 10; Apr 7; Apr 28
Task Completed 100% On-Time
Task Completed Satsifactorily, but delivered < 1 week late
Delayed- Non Critical
Delayed- Critical
Scheduled Time
Delayed Scheduled Time
Critical Path- These tasks must be completed on time
EXAMPLE - Week of June 10, Project Approval is a week late and on Week of July 8 the Interim Report is three days late
| June | Feb 10: July
| 3 |  | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29
Submit Proposal to Advisor
Submit Proposal to Sponsor (if appropriate)
Project Approval | bar: 10 to 17
Project Kick Off | bar: 10
Weekly Status | bar: 17 to 24; July 8 to July 15
Interim Report | bar: July 1
Final Report Draft & Presentation Draft | bar: July 15
Oral Presentation | bar: July 22 to July 29
Final Report | bar: July 29
You are here -->

## RACI
Artifact: | RACI CHART
Project Name: | Invoice and Inventory Management
|  |  | Bala rama krishna peddi | Mohammed yaqoob
| Index | Tasks
|  | Invoice and Inventory Management | Role | Role
| 1 | Capstone Project Registration
| 1.1 | Submit propsal
| 1.2 | Topical approval
| 1.3 | Course registration | R | R
| 2 | Orientation
| 2.1 | Attend Orientation class |  | R
| 2.2 | Complete Orientataion class | R | R
| 2.3 | Read all canvas Information | R | R
| 3 | Assignments
| 3.1 | Final propsal | R | A
| 3.2 | Complete outline | A | R
| 3.3 | Weekly status | A | R
| 3.4 | Interm report | R | A
| 3.5 | final report | A | R
| 3.6 | Final presentation | R | R
| 3.7 | Oral Presentation | R | R
| 4 | Development
| 4.1 | Authentication page
| 4.2 | Navbar for admin user | C | R
| 4.3 | Login for admin | R | C
| 4.4 | Logout Functionality | C | R
| 4.5 | Registration Page for users | R | A
| 4.6 | Login for Users | A | R
| 4.7 | view profile for user | R | A
| 4.8 | Change password for user | R | A
| 4.9 | Logout Functionality for User | R | A
| 5 | User and admin Functionality
| 5.1 | Add product from | R | A
| 5.2 | Accept user request by admin when created auser | A | R
| R = | Responsible - those who do the work to complete the task
| A = | Accountable - one person answerable for completion of the task (approves R's work)
| C = | Consulted - look to for opinions, such as subject matter experts (SMEs)
| I = | Informed - those to keep up-to-date